## Sheet1
Debugging List
# | Issue | Severity | Area | Status
1 | Dashboard does not display current store name | Low | UI / Dashboard | ✅ Fixed
2 | Date format shows too much precision (2026-05-18 19:23:24.530646) | Low | UI / Formatting | ✅ Fixed
3 | Flash message pushed layout/container | Low | UI | ✅ Fixed
4 | Warehouse user redirected to wrong dashboard/navbar | Medium | Auth / Navigation | ✅ Fixed
5 | Pending workflow (assistant → manager approval) | High | Orders Workflow | ✅ Passed
6 | sqlite3 database is locked when manager submits pending order | HIGH | Database / Transactions | Open
7 | Warehouse login welcome message missing | Low | UX | ✅ Fixed
8 | Success flash messages too plain / ugly | Low | UI / UX | ✅ Fixed
9 | Missing “Add Category” functionality | Medium | Products Module | ✅ Fixed
10 | Search UX unclear — no reset/back button | Low | UX | ✅ Fixed
11 | Product update flash message styling poor | Low | UI / UX | ✅ Fixed
12 | Disable / Enable does not properly update is_active in DB | Medium | Products / Database | Open
13 | Warehouse stock NOT reduced after submitted order | HIGH | Inventory Logic | Open
14 | No stock validation before order submission | HIGH | Business Logic | Open